## Sheet1
Date | Manhours | Description | Iteration | Feature | Comment | Cost | Developer Salary | 25000
2019-02-07 | 2 | Planning | 1 | Persona | Who is the app for? | 29 | Working Weeks | 46
2019-02-07 | 2 | Planning | 1 | User Journey | What do they want to do ? | 29 | Hours per week | 37.5
2019-02-07 | 2 | Planning | 1 | A3 Mapping/Book | Basically a tidy up of class notes & train palaver | 29 | Est Hourly Rate | 14.4928
2019-02-08 | 1 | Planning | 1 | Digitise Plans | Renaming app, applying notes to readme file | 14.5 |  | 14.5
2019-02-08 | 1 | Design | 1 | Setup Environment | Creating file structure, setting up git and committing along the way | 14.5
2019-02-08 | 1 | Design | 1 | Setup Database | Create DB, Create Schema, Create Seed data | 14.5 | Total Hours
2019-02-08 | 1 | Implementation | 1 | Merchant – CRUD | Created merchant test spec and merchant model class | 14.5 | Total Cost
2019-02-08 | 0.25 | Implementation | 1 | Tag – CRUD | Created tag test spec and tag model class | 3.625
2019-02-08 | 1 | Implementation | 1 | Transactions – CRUD | Created transaction test spec and transaction model class | 14.5
2019-02-08 | 2 | Design | 1 | Wireframing | Before proceeding with views draw up wireframe using fixed model classes | 29
2019-02-08 | 1 | Implementation | 1 | Create Layout, Main Controller | Need to ask about that auto complete html header thing?
2019-02-08 | 1 | Implementation | 1 | Create Layout, Main Controller | Created structure ^ stitch in time. Content still basic.
2019-02-08 | 1 | Implementation | 1 | Create Transaction Controller | Requirements – don’t forget they’re up there and matter!
2019-02-08 | 0.25 | Implementation | 1 | Create Merchant Controller | basically a copy of above, tested.
2019-02-08 | 0.25 | Implementation | 1 | Create Tag Controller | basically a copy of above, tested.
2019-02-08 | 1 | Implementation | 1 | Create Transaction Functionality | Little bit of bother remembering which name points to the db
2019-02-08 | 0.25 | Implementation | 1 | Create Tag Functionality | Once you’ve done one…
2019-02-08 | 0.25 | Implementation | 1 | Create Merchant Functionality | Once you’ve done one…