## Reporting
Date | Manhours | Description | Iteration | Feature | Comment | Cost | Developer Salary | 25000
2019-02-07 | 2 | Planning | 1 | Persona | Who is the app for? | 29 | Working Weeks | 46
2019-02-07 | 2 | Planning | 1 | User Journey | What do they want to do ? | 29 | Hours per week | 37.5
2019-02-07 | 2 | Planning | 1 | A3 Mapping/Book | Basically a tidy up of class notes & train palaver | 29 | Est Hourly Rate | 14.4928
2019-02-08 | 1 | Planning | 1 | Digitise Plans | Renaming app, applying notes to readme file | 14.5 |  | 14.5
2019-02-08 | 1 | Design | 1 | Setup Environment | Creating file structure, setting up git and committing along the way | 14.5
2019-02-08 | 1 | Design | 1 | Setup Database | Create DB, Create Schema, Create Seed data | 14.5 | Total Hours | 56.5
2019-02-08 | 1 | Implementation | 1 | Merchant – CRUD | Created merchant test spec and merchant model class | 14.5 | Total Cost | 819.25
2019-02-08 | 0.25 | Implementation | 1 | Tag – CRUD | Created tag test spec and tag model class | 3.625
2019-02-08 | 1 | Implementation | 1 | Transactions – CRUD | Created transaction test spec and transaction model class | 14.5
2019-02-08 | 2 | Design | 1 | Wireframing | Before proceeding with views draw up wireframe using fixed model classes | 29
2019-02-08 | 1 | Implementation | 1 | Create Layout, Main Controller | Need to ask about that auto complete html header thing? | 14.5
2019-02-08 | 1 | Implementation | 1 | Create Layout, Main Controller | Created structure ^ stitch in time. Content still basic. | 14.5
2019-02-08 | 1 | Implementation | 1 | Create Transaction Controller | Requirements – don’t forget they’re up there and matter! | 14.5
2019-02-08 | 0.25 | Implementation | 1 | Create Merchant Controller | basically a copy of above, tested. | 3.625
2019-02-08 | 0.25 | Implementation | 1 | Create Tag Controller | basically a copy of above, tested. | 3.625
2019-02-08 | 1 | Implementation | 1 | Create Transaction Functionality | Little bit of bother remembering which name points to the db | 14.5
2019-02-08 | 0.25 | Implementation | 1 | Create Tag Functionality | Once you’ve done one… | 3.625
2019-02-08 | 0.25 | Implementation | 1 | Create Merchant Functionality | Once you’ve done one… | 3.625
2019-02-09 | 0.5 | Implementation | 1 | Create find merchant functionality | Straight forward after doing so much of it | 7.25
2019-02-09 | 0.25 | Implementation | 1 | Create find tag functionality |  | 3.625
2019-02-09 | 0.5 | Implementation | 1 | Create Transaction sum functionality |  | 7.25
2019-02-09 | 1 | Implementation | 1 | Create Edit Merchant functionality | Nightmare owing to being unable to update unless all fields provided | 14.5
2019-02-09 | 0.25 | Implementation | 1 | Create Edit Tag functionality | Once you’ve done one… | 3.625
2019-02-09 | 0.5 | Implementation | 1 | Create Edit Tag functionality | Once you’ve done one…plus bonus dynamic selectors | 7.25
2019-02-09 | 1 | Bugfix | 1 | Transaction.amount_int to float | Well. This is embarrassing. D*ck. Monetary values should be float. Ground up howler. | 14.5
2019-02-09 | 1 | Bugfix | 1 | Transaction total truncating trailing zero | Fixed by converting to string using 2f string formatting | 14.5
2019-02-09 | 1 | Reflection | 1 | Reviewed MVP Version 1 for improvements | Write a list of issues in V1 – what can be improved? | 14.5
2019-02-09 | 2 | Planning | 2 | Discover user needs and measure against time remaining | Have to be careful, play it safe – leave Tue/Wed for CSS malarky. | 29
2019-02-10 | 3 | Planning | 2 | How can you go about meeting above? | What can be done and how can you do it in given time? | 43.5
2019-02-10 | 4 | Design | 2 | Design implementation, order and create rigid ideas | What needs done in which order. Dates. Just dates. Fuck. | 58
2019-02-11 | 0.5 | Implementation | 2 | Remove unecessary ID columns from view | simple enough | 7.25
2019-02-11 | 1 | Implementation | 2 | Add transactions view to merchant model and sum | Sum was a waste as I forgot to access PG object using string | 14.5
2019-02-11 | 0.5 | Implementation | 2 | Add transactions view to tag model and sum | Once you’ve done one…then you spot bugs | 7.25
2019-02-11 | 0.75 | Implementation | 2 | Add budget to tags table, controller, specs and views | Straightforward – planning really helped with this one | 10.875
2019-02-11 | 1 | Implementation | 2 | Add date to transactions table, controller, specs and views | straightforward enough | 14.5
2019-02-11 | 1 | Implementation | 2 | Create struct to hold budget in tag | should have continued with this | 14.5
2019-02-11 | 1 | Implementation | 2 | Display total amount spent per tag per month | ERROR not due to struct but using post rather than get | 14.5
2019-02-11 | 2 | Implementation | 2 | Rebuild a budget class | feels a bit surplus and details not persisted? Would have liked the struct route | 29
2019-02-11 | 1 | Implementation | 2 | show totals for month | straight forward enough | 14.5
2019-02-11 | 0.5 | Implementation | 2 | Create warning/over identifiers for budget | Replace with images later | 7.25
2019-02-11 | 2 | Implementation | 2 | Create Sort Function for Transaction Controller | SQL was not happy with this at all – would not accept params no matter what I did | 29
2019-02-11 | 0.25 | Implementation | 2 | Create Sort Function for Tag Controller | Once you’ve done one… | 3.625
2019-02-11 | 0.25 | Implementation | 2 | Create Sort Function for Merchant Controller | Arguably pointless, done fo consistency | 3.625
2019-02-12 | 0.5 | Implementation | 2 | Merge budget views | No need to have two separate pages if get used creatively | 7.25
2019-02-12 | 0.5 | Implementation | 2 | Create Sort Function for Budget Controller | Once you’ve done one...are sorts always in controller? | 7.25
2019-02-12 | 0.5 | Reflection | 2 | Review views for phase 3 | Put CSV import/export on hold until CSS done, product is stable. | 7.25
2019-02-12 | 6 | Styling | 2 | Understanding/Styling Home page | Battering my heid against a wall trying to comprehend CSS and how it relates to this | 87
2019-02-12 | 2 | Styling | 2 | Styling Tables/Icons | Getting a bit more confident – afraid to do the layout and break it all | 29
2019-02-12 | 2 | Styling | 2 | Styling Tables/Icons | Getting a bit more confident – afraid to do the layout and break it all