## Sheet1
Date | Time Spent (manhours) | Description | Feature | Comment | Cost | Developer Salary | 25000
2019-02-07 | 2 | Planning | Persona | Who is the app for? | 29 | Working Weeks | 46
2019-02-07 | 2 | Planning | User Journey | What do they want to do ? | 29 | Hours per week | 37.5
2019-02-07 | 2 | Planning | A3 Mapping/Book | Basically a tidy up of class notes & train palaver | 29 | Est Hourly Rate | 14.4928
2019-02-08 | 1 | Planning | Digitise Plans | Renaming app, applying notes to readme file | 14.5 |  | 14.5
2019-02-08 | 1 | Design | Setup Environment | Creating file structure, setting up git and committing along the way | 14.5
2019-02-08 | 1 | Design | Setup Database | Create DB, Create Schema, Create Seed data | 14.5
2019-02-08 | 1 | Implementation | Merchant – CRUD | Created test spec and merchant model class | 14.5
2019-02-08 | 0.25 | Implementation | Tag – CRUD | Created test spec and merchant model class
2019-02-08 |  | Implementation