## Sheet1
Date | Manhours | Description | Iteration | Feature | Comment | Cost | Developer Salary | 25000
2019-02-07 | 2 | Planning | 1 | Persona | Who is the app for? | 29 | Working Weeks | 46
2019-02-07 | 2 | Planning | 1 | User Journey | What do they want to do ? | 29 | Hours per week | 37.5
2019-02-07 | 2 | Planning | 1 | A3 Mapping/Book | Basically a tidy up of class notes & train palaver | 29 | Est Hourly Rate | 14.4928
2019-02-08 | 1 | Planning | 1 | Digitise Plans | Renaming app, applying notes to readme file | 14.5 |  | 14.5
2019-02-08 | 1 | Design | 1 | Setup Environment | Creating file structure, setting up git and committing along the way | 14.5
2019-02-08 | 1 | Design | 1 | Setup Database | Create DB, Create Schema, Create Seed data | 14.5 | Total Hours
2019-02-08 | 1 | Implementation | 1 | Merchant – CRUD | Created merchant test spec and merchant model class | 14.5 | Total Cost
2019-02-08 | 0.25 | Implementation | 1 | Tag – CRUD | Created tag test spec and tag model class | 3.625
2019-02-08 | 1 | Implementation | 1 | Transactions – CRUD | Created transaction test spec and transaction model class | 14.5
2019-02-08 | 2 | Design | 1 | Wireframing | Before proceeding with views draw up wireframe using fixed model classes | 29
2019-02-08 | 1 | Implementation | 1 | Create Layout, Main Controller | Need to ask about that auto complete html header thing?
2019-02-08 | 1 | Implementation | 1 | Create Layout, Main Controller | Created structure ^ stitch in time. Content still basic.
2019-02-08 | 1 | Implementation | 1 | Create Transaction Controller | Requirements – don’t forget they’re up there and matter!
2019-02-08 | 0.25 | Implementation | 1 | Create Merchant Controller | basically a copy of above, tested.
2019-02-08 | 0.25 | Implementation | 1 | Create Tag Controller | basically a copy of above, tested.
2019-02-08 | 1 | Implementation | 1 | Create Transaction Functionality | Little bit of bother remembering which name points to the db
2019-02-08 | 0.25 | Implementation | 1 | Create Tag Functionality | Once you’ve done one…
2019-02-08 | 0.25 | Implementation | 1 | Create Merchant Functionality | Once you’ve done one…
2019-02-09 | 0.5 | Implementation | 1 | Create find merchant functionality
2019-02-09 | 0.25 | Implementation | 1 | Create find tag functionality

## Sheet2
“And, baby, when I tell ya the boy has got his own money, I mean the boy has got his own MONEY!”
“I had the most absurd nightmare. I was poor and no one liked me.”
'Show me the MONEY!”
“There’s just one thing I want you to do for me Jerry...”
“I’m gonna teach you to hate spending money.”
“Look, money may be your god but it ain’t mine, alright? I want a warm bath and a cup of tea, over.”
“What would you do if you had a million dollars...”
“Napoleon, you know we can’t afford the fun pack. “
“Greed is good”
"That will be $1.5 million please. I’ll take it in cash, check or a transfer. I’m not greedy. I just want my half."
"No dough, no show."
“There’s no nobility in poverty. I’ve been a poor man, and I’ve been a rich man. And I choose rich every f*cking time.”
“I’m washing lettuce. Soon, I’ll be on fries. In a few years, I’ll make assistant manager, and that’s when the big bucks start rolling in.”
“You fool! You’re 30 cents away from having a quarter!”
“A fool and his money are lucky enough to get together in the first place.”
“The safest way to double your money is to fold it over and put it in your pocket.”
“Man, money ain't got no owners, only spenders”
“Money be GREEN!”
“If you think nobody cares if you’re alive, try missing a couple of car payments.”
“Carpe per diem – seize the check.”
“But you start to follow the money...”
"It takes money to make money, Stringer. Otherwise, hell, every pauper would be a king."
"All the pieces matter."
“It’s all in the game ...”